## Event Info
EVENT DAY RUN OF SHOW
Master coordination document — keep open on every team lead's device
Event Name | [e.g., Annual Customer Summit 2026]
Event Date | [MM/DD/YYYY]
Venue | [Venue name + address]
Doors Open | [Time]
Program Start | [Time]
Program End | [Time]
Load-Out Complete | [Time]
Expected Attendance | [#]
KEY CONTACTS
Event Lead | [Name] · [Phone] · [Email]
Production Lead | [Name] · [Phone] · [Email]
Venue Contact | [Name] · [Phone] · [Email]
AV Lead | [Name] · [Phone] · [Email]
Catering Lead | [Name] · [Phone] · [Email]
Security | [Name] · [Phone] · [Email]
Medical / First Aid | [Name + location]
Expo Pass Support | 312-585-7582
CRITICAL INFO
WiFi Network / Password | [Network] / [Password]
Emergency Assembly Point | [Location]
Nearest Hospital | [Name + address]
Radio Channels | Ch 1: Production · Ch 2: Ops · Ch 3: Security
HOW TO USE THIS WORKBOOK
1. Event Info | Fill in first — populates the rest of the workbook
2. Locations | List every venue space (feeds Run of Show dropdowns)
3. Team & Contacts | Fill roster (feeds Owner dropdowns + auto-fills phones)
4. Run of Show | Main minute-by-minute timeline
5. Cue Sheet | Stripped-down view for whoever is calling the show
6. Load-In/Out | Gear arrival/departure, truck manifest
7. Vendors | External vendor schedule, separate from internal team
8. Contingencies | Pre-decided responses to likely problems
9. Debrief | Fill in post-event while memory is fresh
#VALUE!

## Locations
VENUE LOCATIONS
Standardize location names here — feeds dropdowns in Run of Show, Cue Sheet, and Load-In/Out
Location Name | Capacity | Notes
Loading Dock |  | Truck access, ground level
Lobby | 300 | Registration + pre-function
Pre-function Area | 400 | Catering, networking
Main Ballroom | 800 | Main stage, keynotes, panel
Room A | 120 | Breakout track 1
Room B | 120 | Breakout track 2
Room C | 80 | Breakout track 3
Green Room | 20 | Speaker prep, VIP
Reception Space | 400 | Evening reception
Back of House |  | Production, storage

## Team & Contacts
TEAM ROSTER & CONTACT SHEET
Fill in Role + Name + Phone — Run of Show will auto-populate phone numbers from this sheet
Role | Name | Phone | Email | Radio Ch | On-Site Hours | Responsibilities
Event Lead |  |  |  | Ch 1 | 05:00 – 20:30 | Overall event ownership, final decisions, client-facing
Production Lead |  |  |  | Ch 1 | 04:00 – 20:30 | AV, staging, technical production, load-in/out
AV Lead |  |  |  | Ch 1 | 05:00 – 20:00 | Audio, video, lighting, slides, mics
Stage Manager |  |  |  | Ch 1 | 08:00 – 16:30 | Calls the show — cues speakers, mics, slides, music
Registration Lead |  |  |  | Ch 2 | 07:00 – 12:00 | Check-in, badges, walk-ins, VIP handling
Catering Lead |  |  |  | Ch 2 | 07:00 – 18:00 | All F&B service, dietary requests, timing
Emcee |  |  |  | Ch 1 | 09:00 – 16:00 | On-stage transitions, announcements, hosting
Session Lead – Room A |  |  |  | Ch 2 | 12:30 – 15:00 | Breakout room management, speaker support
Session Lead – Room B |  |  |  | Ch 2 | 12:30 – 15:00 | Breakout room management, speaker support
Session Lead – Room C |  |  |  | Ch 2 | 12:30 – 15:00 | Breakout room management, speaker support
Security Lead |  |  |  | Ch 3 | 06:00 – 20:30 | Access control, guest safety, incident response
Volunteer Coordinator |  |  |  | Ch 2 | 06:00 – 19:00 | Volunteer check-in, assignments, breaks
Venue Contact |  |  |  | — | All day | Venue-side liaison, facilities issues
Comms Lead |  |  |  | Ch 2 | 08:00 – 18:00 | Attendee app pushes, signage, social updates

## Run of Show
RUN OF SHOW — MINUTE-BY-MINUTE TIMELINE
★ = Critical Path (cannot slip). Phone auto-fills from Team & Contacts. Insert 'Buffer' rows liberally — they're insurance.
Start | End | Dur | Phase | ★ | Task / Cue | Owner | Owner Phone | Support | Location | Comms | Status
05:00 | 06:00 | 1:00 | Setup | ★ | Unload all production gear from trucks into venue loading dock | Production Lead | 0 | AV team, Venue ops | Loading Dock |  | Not Started
06:00 | 08:00 | 2:00 | Setup | ★ | Build main stage, rig screens, run audio cables, position speakers | AV Lead | 0 | Production crew (4) | Main Ballroom |  | Not Started
07:00 | 09:00 | 2:00 | Setup |  | Set registration tables, laptops, badge printers, signage | Registration Lead | 0 | Volunteers (3) | Lobby |  | Not Started
08:00 | 09:00 | 1:00 | Setup |  | Deliver and arrange breakfast stations, coffee, tables | Catering Lead | 0 | Venue F&B | Pre-function Area |  | Not Started
09:00 | 09:30 | 0:30 | Rehearsal | ★ | Walk through every speaker transition, test all mics, verify slide advance | Production Lead | 0 | AV Lead, Speakers, Stage Manager | Main Ballroom |  | Not Started
09:30 | 09:45 | 0:15 | Buffer |  | BUFFER — float time for rehearsal overrun or last-minute fixes | Event Lead | 0 |  | Main Ballroom |  | Not Started
09:45 | 10:00 | 0:15 | Rehearsal | ★ | All-hands briefing — full team walkthrough of run-of-show and contingencies | Event Lead | 0 | All team leads | Green Room |  | Not Started
10:00 | 10:30 | 0:30 | Live | ★ | DOORS OPEN — registration live | Registration Lead | 0 | Volunteers, Security | Lobby | App push: 'Doors are open, welcome!' | Not Started
10:30 | 10:45 | 0:15 | Live |  | Hold music + lobby announcements directing guests to ballroom | AV Lead | 0 | Emcee | Lobby | Signage live; emcee announce every 5 min | Not Started
10:45 | 11:00 | 0:15 | Live | ★ | Opening: emcee welcomes, covers WiFi, emergency exits, agenda | Emcee | 0 | Stage Manager | Main Ballroom | WiFi info on screen + in app | Not Started
11:00 | 11:45 | 0:45 | Live | ★ | Keynote: [Speaker Name] | Emcee | 0 | Stage Manager, Speaker handler | Main Ballroom |  | Not Started
11:45 | 12:00 | 0:15 | Live |  | Transition + break announcement | Emcee | 0 | AV Lead | Main Ballroom | App push: 'Lunch now in Pre-function' | Not Started
12:00 | 13:00 | 1:00 | Live |  | Networking lunch | Catering Lead | 0 | Volunteers | Pre-function Area | Background music on | Not Started
13:00 | 14:30 | 1:30 | Live |  | Breakout sessions (3 tracks) | Session Lead – Room A | 0 | AV team (3), Session Leads B & C | Room A | App push at 12:50 with track locations | Not Started
14:30 | 14:45 | 0:15 | Live |  | Coffee break | Catering Lead | 0 | Volunteers | Pre-function Area |  | Not Started
14:45 | 15:30 | 0:45 | Live | ★ | Panel discussion — moderated + audience Q&A | Emcee | 0 | AV Lead, Stage Manager | Main Ballroom |  | Not Started
15:30 | 15:45 | 0:15 | Live |  | BUFFER — float for Q&A overrun | Event Lead | 0 |  | Main Ballroom |  | Not Started
15:45 | 16:00 | 0:15 | Live | ★ | Closing remarks + thank you — sponsors acknowledged | Event Lead | 0 | Emcee | Main Ballroom | App push: 'Reception starting at 16:00' | Not Started
16:00 | 18:00 | 2:00 | Live |  | Networking reception | Catering Lead | 0 | AV, Volunteers | Reception Space |  | Not Started
18:00 | 20:00 | 2:00 | Teardown | ★ | Strike: teardown + load-out. Break down stage, AV, registration. Load trucks. | Production Lead | 0 | AV team, Volunteers | Main Ballroom |  | Not Started
20:00 | 20:30 | 0:30 | Teardown | ★ | Final walkthrough + venue signoff with venue contact | Event Lead | 0 | Venue Contact | Main Ballroom |  | Not Started
Note on E4: Mark with ★ if this task CANNOT slip without cascading failure. Keep to 5-8 items max — if everything is critical, nothing is.
Note on F4: Write what happens, not just what's scheduled. Include the trigger and handoff. Cues should be specific enough a substitute could run them.
Note on H4: Auto-fills from Team & Contacts sheet based on Owner. Fill the Team sheet first.
Note on K4: What gets communicated to attendees at this moment — app push, signage change, emcee announcement.

## Cue Sheet
CUE SHEET — FOR THE PERSON CALLING THE SHOW
Stripped-down minute-by-minute. Mic cues · music cues · slide advances · scripted lines. Print this. Hold it in your hand.
Time | Cue # | Type | Cue / Action | Scripted Line (verbatim) | Standby Before | ✓
10:44 | Q1 | Music | Fade out walk-in music over 10 sec |  | 10:43
10:45 | Q2 | Lights | House down 50%, stage up full |  | 10:44
10:45 | Q3 | Mic | Emcee handheld live |  | 10:44
10:45 | Q4 | Script | Emcee enters stage right | "Good morning everyone, and welcome to [Event Name]..." | 10:44
10:48 | Q5 | Slide | Advance to slide 2 (Agenda) |  | 10:47
10:52 | Q6 | Slide | Advance to slide 3 (Housekeeping) |  | 10:51
10:58 | Q7 | Script | Emcee introduces keynote speaker | "It's my great pleasure to introduce..." | 10:57
11:00 | Q8 | Mic | Swap to keynote lavalier, kill handheld |  | 10:59
11:00 | Q9 | Lights | Preset: keynote look |  | 10:59
11:00 | Q10 | Slide | Load keynote deck, slide 1 |  | 10:58
11:42 | Q11 | Standby | 3-min warning to speaker via confidence monitor |  | 11:39
11:45 | Q12 | Mic | Emcee handheld live, thank speaker | "Thank you so much [Name], that was incredible..." | 11:44
11:47 | Q13 | Music | Break music up (bed, -10dB under VO) |  | 11:46
11:48 | Q14 | Script | Emcee announces lunch | "Lunch is being served in the pre-function area. We'll resume at 1pm sharp in this room." | 11:47
14:44 | Q15 | Music | Fade out break music |  | 14:43
14:45 | Q16 | Lights | Panel preset — 4 chairs lit, moderator mark |  | 14:44
14:45 | Q17 | Mic | 4 lavs + moderator handheld live |  | 14:40
14:45 | Q18 | Script | Emcee intros panel | "Please welcome our panelists for today's discussion..." | 14:44
15:43 | Q19 | Standby | 2-min warning to moderator |  | 15:41
15:45 | Q20 | Mic | Emcee handheld live for closing |  | 15:44
15:45 | Q21 | Script | Closing remarks | "Before we wrap up, I want to thank our sponsors..." | 15:44
15:58 | Q22 | Script | Invite to reception | "Please join us next door for the reception. Safe travels home." | 15:57
16:00 | Q23 | Music | Play-out music up full |  | 15:59
16:00 | Q24 | Lights | House up full, stage out |  | 15:59
Note on E4: If there's a line that MUST be said verbatim — sponsor acknowledgment, legal, safety — put it here word-for-word.
Note on F4: When standby warning goes to the operator — typically 60 seconds before Go.

## Load-In & Out
LOAD-IN & LOAD-OUT MANIFEST
Gear arrivals, truck manifest, signoffs. This is where events bleed money — track every case.
Time | Direction | Item / Case | Qty | From / To | Truck / Vehicle | Received By | Condition / Notes
04:30 | In | Stage deck — 4x8 platforms | 12 | ABC Staging | Truck 1
04:30 | In | Stage skirt + steps | 1 set | ABC Staging | Truck 1
05:00 | In | Main PA — L/R line arrays | 2 | XYZ Audio | Truck 2
05:00 | In | Subwoofers | 4 | XYZ Audio | Truck 2
05:00 | In | Amp rack + console | 1 | XYZ Audio | Truck 2
05:00 | In | Mic kit (lavs, handhelds, headset) | 1 kit | XYZ Audio | Truck 2
05:30 | In | LED wall panels | 24 | XYZ Audio | Truck 2
05:30 | In | Video processor + playback laptop | 1 kit | XYZ Audio | Truck 2
06:00 | In | Lighting trusses + motors | 2 sets | Bright Light Co | Truck 3
06:00 | In | Moving heads + wash fixtures | 24 | Bright Light Co | Truck 3
07:00 | In | Registration laptops + printers | 4 | Client office | Van A
07:00 | In | Badge stock + lanyards | 800 | Client office | Van A
07:00 | In | Signage + banners | 1 set | Print vendor | Van B
08:00 | In | Gift bags | 800 | Fulfillment vendor | Van C
18:00 | Out | LED wall panels | 24 | Return XYZ Audio | Truck 2
18:30 | Out | Main PA + subs + amps | complete | Return XYZ Audio | Truck 2
19:00 | Out | Lighting | complete | Return Bright Light Co | Truck 3
19:30 | Out | Stage deck + skirt | complete | Return ABC Staging | Truck 1
20:00 | Out | Registration + signage + remaining gift bags | — | Return client office | Van A
Note on G4: Initials of person who physically received/signed for the item. This is the audit trail if something's missing.

## Vendors
VENDOR SCHEDULE
External vendors — separate from internal team. Includes COI status, arrival, parking/dock assignment.
Vendor | Service | On-Site Contact | Phone | Arrival | Departure | Dock / Parking | COI on File | Notes
ABC Staging | Stage build |  |  | 04:30 | 20:00 | Dock 1 | Yes | Arriving before venue opens — meet at dock
XYZ Audio | AV / LED wall |  |  | 05:00 | 19:00 | Dock 1 | Yes
Bright Light Co | Lighting |  |  | 06:00 | 19:30 | Dock 2 | Yes
Elegant Eats Catering | F&B all day |  |  | 07:00 | 18:30 | Kitchen entrance | Yes | 4 service moments — see Run of Show
Print Plus | Signage |  |  | 07:00 | 08:00 / 20:00 | Dock 2 | Yes | Drop + return
Sparkle Floral | Floral / décor |  |  | 07:30 | 09:00 / 18:00 | Front entry | Yes
Summit Security | Event security |  |  | 06:00 | 20:30 | All entries | Yes | Full team, 6 officers
MediCorp | On-site medic |  |  | 09:00 | 18:00 | Designated station | Yes | Located off Pre-function
Digital Frame | Photo/video |  |  | 09:00 | 17:00 | Visitor parking | No
TechStream | Live streaming |  |  | 06:00 | 17:00 | Dock 1 | Yes | Coordinate with AV Lead
Giveaway Co | Gift bags |  |  | 08:00 |  | Van C | N/A | Drop only
Note on H4: Certificate of Insurance. 'No' = vendor should not be on site. Follow up before event day.

## Contingencies
CONTINGENCY PLAYBOOK
Decide once, react fast. Section A: common scenarios. Section B: YOUR event's specific risks (fill these in).
Scenario | Likelihood | Trigger / Signal | Response Plan | Decision Owner
SECTION A — COMMON SCENARIOS (pre-filled, adapt as needed)
Speaker is late or no-show | Medium | Speaker not on site 30 min before their slot; not reachable by phone | 1. Emcee extends previous segment or starts Q&A early. 2. Swap in backup speaker or pre-recorded content. 3. Rearrange running order — shift next session forward. 4. Event Lead makes go/no-go call 15 min before slot. | Event Lead
AV failure (audio cuts out) | Medium | Mic, speakers, or playback system loses signal mid-program | 1. AV Lead switches to backup mic / secondary audio path. 2. Emcee ad-libs and acknowledges issue calmly. 3. If unresolved in 3 min: break early, push schedule. 4. AV Lead radios Production Lead for parts. | AV Lead
Projector / screen failure | Medium | Slides stop advancing, screen goes black, HDMI signal lost | 1. Speaker continues without slides (briefed in advance this is acceptable). 2. AV swaps laptop / cable / adapter. 3. Use backup screen or TV monitor. 4. Last resort: distribute printed slide handouts. | AV Lead
Running behind schedule | High | Current session ending 10+ min late; cascading delay | 1. Shorten next break by half. 2. Event Lead + Emcee decide which segment to compress. 3. Communicate change to next speaker privately. 4. Never cut catering breaks entirely — shorten instead. | Event Lead
Running ahead of schedule | Medium | Current session ending 10+ min early | 1. Extend Q&A or networking break. 2. Do NOT move up next speaker without their awareness. 3. Emcee fills time with pre-prepared content. | Emcee
Registration backup / long lines | Medium | Line exceeds 20 people or wait exceeds 10 min | 1. Open additional check-in station. 2. Pull volunteers from other stations. 3. If program start approaching: begin seating unregistered guests, process badges inside. | Registration Lead
Medical emergency | Low | Any guest or staff requires medical attention | 1. First aid responder goes to person. 2. Security clears space. 3. If serious: call 911, notify Event Lead. 4. Designated team member meets EMS at entrance. 5. Program continues unless evacuation needed. | Security Lead
Fire alarm / evacuation | Low | Alarm sounds or venue issues evacuation order | 1. Emcee announces calmly from stage, directs to nearest exits. 2. Team leads sweep assigned areas. 3. All staff meet at Assembly Point. 4. Event Lead coordinates with venue + authorities. | Event Lead
Catering delay or shortage | Medium | Food not ready at scheduled time, or running short | 1. Catering Lead assesses ETA. 2. Emcee extends current session or starts break activity early. 3. If shortage: prioritize registered attendees. 4. Communicate transparently. | Catering Lead
Weather disruption | Variable | Rain, extreme heat, wind during outdoor portions | 1. Activate pre-identified indoor backup space. 2. Communicate via app / signage / emcee. 3. Adjust timing for transition. 4. Trigger decision by [time] — no later. | Event Lead
Sponsor / VIP complaint | Medium | Sponsor or VIP flags dissatisfaction | 1. Event Lead handles personally — not a junior team member. 2. Listen fully, acknowledge, fix what's fixable. 3. Follow up within 24 hrs regardless of resolution. | Event Lead
Internet / WiFi failure | Medium | Venue WiFi drops; registration or streaming affected | 1. Switch registration to offline mode (pre-loaded attendee list). 2. Use mobile hotspots for critical devices. 3. If streaming: pause, announce resumption via social. | Production Lead
SECTION B — YOUR EVENT-SPECIFIC RISKS (answer the prompts below)
PROMPT: What are the 3 things most likely to go wrong at YOUR event that aren't on the list above? |  |  | Examples: key sponsor's CEO is flying in morning-of (flight delay?). Product demo requires specific model not yet shipped. Controversial speaker may draw protesters. Client's logo printed wrong on step-and-repeat. Key volunteer group is unreliable. Venue is mid-renovation. Permit issue outstanding.
YOUR RISK #1
YOUR RISK #2
YOUR RISK #3
PROMPT: What's the 'single point of failure' on your event — the one thing where, if it fails, the whole event fails? |  |  | Examples: the livestream (for hybrid events), the keynote speaker, the product reveal, the client's approval at 3pm. Whatever it is, it gets triple redundancy.
YOUR SPOF
PROMPT: If your venue suddenly became unusable 4 hours before the event, what would you do? |  |  | Even a rough answer is better than improvising in the moment. Who makes the call? Is there a backup venue? How do you notify attendees?
YOUR VENUE PLAN B

## Debrief
POST-EVENT DEBRIEF
Fill within 48 hrs while memory is fresh. This is how your next event gets better.
Debrief Date
Attendees of Debrief
BY THE NUMBERS
Attendance (target vs actual)
No-show rate
NPS / attendee survey score
Speaker feedback
Sponsor feedback
Budget (target vs actual)
Incidents logged
WHAT WENT WELL
Biggest win
Processes that worked
People / vendors to work with again
Moments the team should be proud of
WHAT WENT WRONG
Biggest miss
Near-misses (things that almost went wrong)
Where the Run of Show broke down
Contingencies we actually needed to use
Gaps we hadn't planned for
WHAT WE'D DO DIFFERENTLY
START doing next time
STOP doing next time
CONTINUE doing next time
VENDOR / PARTNER REVIEW
Keep (performed above expectation)
Caution (acceptable but watch)
Replace (performed below expectation)
ACTION ITEMS FOR NEXT EVENT
Action 1
Action 2
Action 3
Action 4
Action 5